## Helpers
Milestones			Bank Holiday		Leave
			25/12/18		24/12/18
			26/12/18		27/12/18
			01/01/19		31/12/18
			19/04/19		02/01/19
			22/04/19		03/01/19
			06/05/19		07/01/19
			27/05/19		23/04/19
			26/08/19		24/04/19
			25/12/19		25/04/19
			26/12/19		28/05/19
					29/05/19
Platform					30/05/19
					15/07/19
Version 1					16/07/19
					17/07/19
					18/07/19
					22/07/19
					23/07/19
					24/07/19
					25/07/19

## issues
Issues	Milestone	Title	Description	Estimate	Due Date
32	Platform	Task One	A description of Task One.	14400	11/12/18
34	Platform	Task Two	A description of Task Two.	7200	11/12/18
33	Platform	Task Three	A description of Task Three.	10800	11/12/18
35	Platform	Task Four	A description of Task Four.	14400	12/12/18
36	Platform	Task Five	A description of Task Five.	28800	13/12/18
37	Platform	Task Six	A description of Task Six.	7200	13/12/18
38	Platform	Task Seven	A description of Task Seven.	14400	14/12/18
39	Platform	Task Eight	A description of Task Eight.	57600	18/12/18
40	Platform	Task Nine	A description of Task Nine.	57600	20/12/18
42	Platform	Task Ten	A description of Task Ten.	57600	16/01/19
8	Platform	Task Eleven	A description of Task Eleven.	57600	22/01/19
3	Platform	Task Twelve	A description of Task Twelve.	144000	23/01/19
5	Version 1	Task Thirteen	A description of Task Thirteen.	86400
6	Version 1	Task Fourteen	A description of Task Fourteen.	86400

## Gantt
		Start Date					50					51					52					01					02					03					04					05					06					07					08					09					10					11					12					13					14					15					16					17					18					19					20					21					22					23
		10-Dec-2018					Dec-18					Jan-19					Feb-19					Mar-19					Apr-19					May-19					Jun-19
	Milestone	Start Date	1	Issue Id	Estimate	Due Date	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08
	Platform	10-Dec-2018	2	32	0.5	11-Dec-2018
		10-Dec-2018	3	34	0.25	11-Dec-2018
		10-Dec-2018	4	33	0.375	11-Dec-2018
		12-Dec-2018	5	35	0.5	12-Dec-2018
Task		13-Dec-2018	6	36	1	13-Dec-2018
Bank Holiday		13-Dec-2018	7	37	0.25	13-Dec-2018
Weekend		17-Dec-2018	8	38	0.5	14-Dec-2018
Leave		17-Dec-2018	9	39	2	18-Dec-2018
		19-Dec-2018	10	40	2	20-Dec-2018
		24-Dec-2018	11	42	2	16-Jan-2019
		17-Jan-2019	12	8	2	22-Jan-2019